## Traveler Master Routing
Sequence | Workstation / Subcontractor | Manufacturing Instructions | Est Setup (h) | Est Run (h) | Total Hrs | Transit Buffer (Days) | Sign-off
010 | Sawing Cut-Off Bay | Cut bar stock to 210mm billet length | 0.25 | 0.75 |  | 0 | INITIALED
020 | CNC Lathe NLX-2500 | Turn OD, bore ID, single-point ACME thread | 1.5 | 4.2 |  | 0 | INITIALED
030 | 5-Axis Mill DMU-50 | Mill cross-holes and trunnion mounting ears | 2 | 6.5 |  | 0 | IN PROGRESS
040 | Bodycote Thermal Subcontract | Vacuum Heat Treat to 52-54 HRC | 0 | 0 |  | 4 | SCHEDULED
050 | CNC Cylindrical Grinding | Finish grind seal diameter to 25.000 +0/-0.005mm | 1 | 3.8 |  | 0 | QUEUED
060 | CMM Quality Inspection | 100% feature verification against AS9102 Form 3 | 0.75 | 2 |  | 0 | QUEUED

## Traceability & Certs
Work Order Traveler # | TRV-2026-4402
Customer Purchase Order | PO-988310-ENG
Material Spec | AMS 5643 / 17-4 PH Stainless Steel Condition H1150
Mill Heat Number | MHT-88204-REV
Raw Material Cert Attached | YES (Doc # MC-4402-A)
Special Process Class | Aerospace Flight Critical
ITAR / Export Controlled | YES (Strict Facility Chain of Custody)
First Article Inspection (FAI) | Required (AS9102 Standard)