## Weekly Machine Schedule
Machine ID | Machine Name / Cell | Shift Pattern | Gross Daily Hrs | Days / Week | Gross Wkly Hrs | Maint. Buffer (Hrs) | Net Finite Cap (Hrs) | Scheduled Load (Hrs) | Utilization % | Status
CNC-01 | Haas VF-4 3-Axis Mill | 2 Shifts (8h) | 16 | 5 |  | 4 |  | 68.5
CNC-02 | Doosan DNM 5700 Mill | 2 Shifts (8h) | 16 | 5 |  | 4 |  | 72
CNC-03 | Mori Seiki NLX 2500 Lathe | 1 Shift (8h) | 8 | 5 |  | 2 |  | 34
CNC-04 | DMG Mori 5-Axis DMU 50 | 2 Shifts (8h) | 16 | 5 |  | 6 |  | 78
FAB-01 | Trumpf TruBend 5130 Brake | 1 Shift (8h) | 8 | 5 |  | 3 |  | 36.5
FAB-02 | Amada Ensis 3015 Laser | 2 Shifts (8h) | 16 | 5 |  | 5 |  | 71
EDM-01 | Mitsubishi MV2400 Wire EDM | Lights-Out (24h) | 24 | 7 |  | 8 |  | 145
WELD-01 | TIG / MIG Fabrication Cell | 1 Shift (8h) | 8 | 5 |  | 2 |  | 31

## Active Job Queue
Job ID | Customer | Part Number | Part Description | Target Machine | Batch Qty | Setup Min | Unit Run Min | Total Job Hrs | Promised Due Date | Status
WO-8421 | Aerospace Dynamics | AD-7075-MN | Hydraulic Manifold Block | CNC-04 | 25 | 90 | 42.5 |  | 2026-09-04 | In Progress
WO-8422 | Apex Motorsport | APX-CAM-02 | Billet Camshaft Carrier | CNC-01 | 12 | 60 | 28 |  | 2026-09-05 | Queued
WO-8423 | Vanguard Medical | VM-TIT-09 | Titanium Orthopedic Bracket | CNC-04 | 50 | 120 | 18 |  | 2026-09-08 | Queued
WO-8424 | Precision Robotics | PR-ARM-104 | 6061 Articulation Link | CNC-02 | 40 | 45 | 14.5 |  | 2026-09-07 | In Progress
WO-8425 | HydraFlow Valves | HF-BRS-55 | Brass High-Pressure Spool | CNC-03 | 150 | 45 | 4.2 |  | 2026-09-06 | Queued
WO-8426 | Quantum Industrial | QI-ENC-01 | Laser Cut Chassis Plate | FAB-02 | 80 | 20 | 3.8 |  | 2026-09-04 | Completed
WO-8427 | Quantum Industrial | QI-ENC-02 | Formed Enclosure Bracket | FAB-01 | 80 | 40 | 2.5 |  | 2026-09-05 | Queued
WO-8428 | ProTool Solutions | PT-DIE-88 | Hardened D2 Trim Die | EDM-01 | 4 | 30 | 240 |  | 2026-09-09 | Running

## Instructions & Best Practices
MACHINE SHOP PRODUCTION SCHEDULING WORKBOOK
Step 1: Configure Workstations | Update the Weekly Machine Schedule tab with your shop floor machines, actual shift hours, and weekly maintenance allowances.
Step 2: Enter Job Work Orders | Input active work orders in the Active Job Queue tab. The total job duration formula calculates total machine hours including setup.
Step 3: Monitor Capacity & Overload | Check column J and K on the schedule tab. Any workstation exceeding 100% capacity is highlighted as Overloaded. Adjust job sequencing to prevent bottleneck delays.
Step 4: Finite vs Infinite Capacity | Never schedule against 100% gross hours. High-mix machine shops require a 15% buffer for tool changeovers, first-off inspection, and minor maintenance.
Step 5: Transitioning to Real-Time | When managing more than 4 machines or multiple daily schedule updates, spreadsheet files suffer from version conflicts. Synctile provides a live digital visual board that updates shop floor screens instantly.