## Shift Handover Master
Machine ID | Machine Name | Active Job # | Customer | Part # | Current Op | Shift Output | Remaining Qty | Machine Status | Critical Handover Notes / Tool Offsets
CNC-01 | Haas VF-4 3-Axis Mill | WO-8840 | Apex Dynamics | APX-CAM-02 | Op 20 Milling | 28 | 22 | RUNNING | Tool 6 endmill replaced at 14:00; wear offset set to -0.015mm. Part dimensions nominal.
CNC-02 | Doosan DNM 5700 Mill | WO-8844 | HydraFlow Valves | HF-BRS-55 | Op 10 Facing | 65 | 85 | RUNNING | Running unattended cycle. Raw brass billets staged at operator bench for night shift.
CNC-03 | Mori Seiki NLX Lathe | WO-8848 | Vanguard Medical | VM-TIT-09 | Setup in Progress | 0 | 50 | SETUP DELAY | Waiting on 16mm carbide boring bar from tool crib. Setup program loaded on USB.
CNC-04 | DMG Mori 5-Axis DMU | WO-8850 | Aerospace Motion | AM-BLT-104 | Op 30 Finishing | 14 | 6 | RUNNING | Job due tomorrow morning. 6 parts remain. Night shift to finish and sign traveler.
FAB-01 | Trumpf TruBend Brake | WO-8852 | Quantum Enclosures | QI-ENC-02 | Bending Flanges | 80 | 0 | COMPLETED | Batch finished, degreased, and moved to assembly staging rack #4.
FAB-02 | Amada Ensis 3015 Laser | WO-8855 | Midwest Metalworks | MM-SHT-20 | Cutting 3mm SS | 12 | 38 | RUNNING | Nitrogen assist pressure at 16 bar. Dual shuttle operating normally. Clean nozzle at 22:00.

## Supervisor Briefing Checklist
Safety Incidents / Near Misses | NONE | No workplace safety incidents reported during daytime rotation.
First-Hour Shift Priorities | CNC-03 Tooling | Retrieve boring bar immediately to clear setup delay on medical titanium batch.
Hot Expedited Work Orders | WO-8850 (Aerospace) | Must finish night cycle and clear CMM inspection by 07:00 tomorrow.
Maintenance Calls Scheduled | FAB-02 Laser | Preventative nozzle inspection and optic wipe down due at mid-shift.
Outgoing Supervisor Signature | Mark Jenkins (Day Lead) | Signed 2026-09-30 17:00
Incoming Supervisor Signature | Dave Vance (Night Lead) | Acknowledged 2026-09-30 17:05