## SMED Event Analysis
Step # | Setup Activity Description | Current Category | Baseline Min | Target Category | Target Min | Time Saved (Min) | Action Plan / Lean Solution
1 | Locate CNC program and load G-code to control | Internal | 12 | External | 0 |  | Pre-stage verified G-code on DNC network before last part finishes
2 | Retrieve job fixtures and clamp bolts from tool crib | Internal | 18 | External | 2 |  | Stage fixture cart at machine 15 minutes before job teardown
3 | Unclamp old vise and clean T-slots on mill table | Internal | 15 | Internal | 8 |  | Use pneumatic air sweep and magnetic bed scraper
4 | Mount and indicate new vise within 0.005mm | Internal | 25 | Internal | 10 |  | Install zero-point receiver plates and sub-plate location dowels
5 | Measure and preset 14 tool heights in machine | Internal | 30 | External | 4 |  | Pre-measure cutters offline in optical toolsetter with RFID tags
6 | Dry run G-code above part at 5% feedrate | Internal | 20 | Internal | 5 |  | Implement CAM collision simulation verification offline
7 | Machine first-off part and wait for CMM inspection | Internal | 35 | External | 10 |  | Operator on-machine probing for first-off critical dimensions

## Financial Value of Recovered Ho
Metric | Value | Notes
Baseline Setup Duration (Min) | 155 Minutes | Total baseline changeover duration
Target SMED Duration (Min) | 39 Minutes | Total post-SMED changeover duration
Duration Reduction % | 74.8% | Percentage of machine stoppage eliminated
Changeovers Per Week (Fleet) | 24 Setups | Total weekly job changeovers across 6 CNC mills
Spindle Hours Recovered / Week | 46.4 Hours | Additional cutting time unlocked
Average Shop Machine Hourly Rate | $110.00 / Hour | Fully burdened spindle cost per hour
Annual Capacity Value Unlocked | $265,408.00 | Annual gross revenue opportunity from saved setups